## D1
WBS ID | Level | Task/Work Package Name | Duration | Dependencies (WBS ID & Name)
1 | Deliverable | Customer Portal Website |  | --
1.1 | Work Package | User Authentication System |  | 1.2 - Database Design
1.1.1 | Task | Design login page wireframes |  | --
1.1.2 | Task | Implement password validation |  | 1.1.1 - Design login page wireframes
1.1.3 | Task | Create user registration form |  | 1.1.1 - Design login page wireframes
1.1.4 | Task | Build forgot password functionality |  | 1.1.2 - Implement password validation
1.2 | Work Package | Database Design & Setup |  | --
1.2.1 | Task | Design database schema |  | --
1.2.2 | Task | Create database tables |  | 1.2.1 - Design database schema
1.2.3 | Task | Set up database connections |  | 1.2.2 - Create database tables
1.2.4 | Task | Create test data |  | 1.2.2 - Create database tables
1.3 | Work Package | Frontend Development |  | 1.1 - User Authentication System
1.3.1 | Task | Create homepage layout |  | --
1.3.2 | Task | Build user dashboard |  | 1.3.1 - Create homepage layout
1.3.3 | Task | Implement responsive design |  | 1.3.2 - Build user dashboard
1.3.4 | Task | Add navigation system |  | 1.3.1 - Create homepage layout
1.3.5 | Task | Integrate authentication UI |  | 1.1 - User Authentication System
1.4 | Work Package | Testing & Quality Assurance |  | 1.3 - Frontend Development
1.4.1 | Task | Write unit tests |  | --
1.4.2 | Task | Perform integration testing |  | 1.4.1 - Write unit tests
1.4.3 | Task | User acceptance testing |  | 1.4.2 - Perform integration testing
1.4.4 | Task | Security testing |  | 1.4.2 - Perform integration testing
1.5 | Work Package | Deployment & Launch |  | 1.4 - Testing & Quality Assurance
1.5.1 | Task | Set up production environment |  | --
1.5.2 | Task | Deploy application |  | 1.5.1 - Set up production environment
1.5.3 | Task | Monitor initial launch |  | 1.5.2 - Deploy application
[Your ID] | [Level] | [Your deliverable/work package/task name] |  | [WBS ID - Task Name] or --
[Your ID] | [Level] | [Your deliverable/work package/task name] |  | [WBS ID - Task Name] or --
[Your ID] | [Level] | [Your deliverable/work package/task name] |  | [WBS ID - Task Name] or --
[Your ID] | [Level] | [Your deliverable/work package/task name] |  | [WBS ID - Task Name] or --
[Your ID] | [Level] | [Your deliverable/work package/task name] |  | [WBS ID - Task Name] or --

## D2
WBS ID | Level | Task/Work Package Name | Duration | Dependencies (WBS ID & Name)
2 | Deliverable | Customer Portal Website |  | --
2.1 | Work Package | User Authentication System |  | 1.2 - Database Design
2.1.1 | Task | Design login page wireframes |  | --
2.1.2 | Task | Implement password validation |  | 1.1.1 - Design login page wireframes
2.1.3 | Task | Create user registration form |  | 1.1.1 - Design login page wireframes
2.1.4 | Task | Build forgot password functionality |  | 1.1.2 - Implement password validation
2.2 | Work Package | Database Design & Setup |  | --
2.2.1 | Task | Design database schema |  | --
2.2.2 | Task | Create database tables |  | 1.2.1 - Design database schema
2.2.3 | Task | Set up database connections |  | 1.2.2 - Create database tables
2.2.4 | Task | Create test data |  | 1.2.2 - Create database tables
2.3 | Work Package | Frontend Development |  | 1.1 - User Authentication System
2.3.1 | Task | Create homepage layout |  | --
2.3.2 | Task | Build user dashboard |  | 1.3.1 - Create homepage layout
2.3.3 | Task | Implement responsive design |  | 1.3.2 - Build user dashboard
2.3.4 | Task | Add navigation system |  | 1.3.1 - Create homepage layout
2.3.5 | Task | Integrate authentication UI |  | 1.1 - User Authentication System
2.4 | Work Package | Testing & Quality Assurance |  | 1.3 - Frontend Development
2.4.1 | Task | Write unit tests |  | --
2.4.2 | Task | Perform integration testing |  | 1.4.1 - Write unit tests
2.4.3 | Task | User acceptance testing |  | 1.4.2 - Perform integration testing
2.4.4 | Task | Security testing |  | 1.4.2 - Perform integration testing
2.5 | Work Package | Deployment & Launch |  | 1.4 - Testing & Quality Assurance
2.5.1 | Task | Set up production environment |  | --
2.5.2 | Task | Deploy application |  | 1.5.1 - Set up production environment
2.5.3 | Task | Monitor initial launch |  | 1.5.2 - Deploy application
[Your ID] | [Level] | [Your deliverable/work package/task name] |  | [WBS ID - Task Name] or --
[Your ID] | [Level] | [Your deliverable/work package/task name] |  | [WBS ID - Task Name] or --
[Your ID] | [Level] | [Your deliverable/work package/task name] |  | [WBS ID - Task Name] or --
[Your ID] | [Level] | [Your deliverable/work package/task name] |  | [WBS ID - Task Name] or --
[Your ID] | [Level] | [Your deliverable/work package/task name] |  | [WBS ID - Task Name] or --

## D3
WBS ID | Level | Task/Work Package Name | Duration | Dependencies (WBS ID & Name)
1 | Deliverable | Customer Portal Website |  | --
1.1 | Work Package | User Authentication System |  | 1.2 - Database Design
1.1.1 | Task | Design login page wireframes |  | --
1.1.2 | Task | Implement password validation |  | 1.1.1 - Design login page wireframes
1.1.3 | Task | Create user registration form |  | 1.1.1 - Design login page wireframes
1.1.4 | Task | Build forgot password functionality |  | 1.1.2 - Implement password validation
1.2 | Work Package | Database Design & Setup |  | --
1.2.1 | Task | Design database schema |  | --
1.2.2 | Task | Create database tables |  | 1.2.1 - Design database schema
1.2.3 | Task | Set up database connections |  | 1.2.2 - Create database tables
1.2.4 | Task | Create test data |  | 1.2.2 - Create database tables
1.3 | Work Package | Frontend Development |  | 1.1 - User Authentication System
1.3.1 | Task | Create homepage layout |  | --
1.3.2 | Task | Build user dashboard |  | 1.3.1 - Create homepage layout
1.3.3 | Task | Implement responsive design |  | 1.3.2 - Build user dashboard
1.3.4 | Task | Add navigation system |  | 1.3.1 - Create homepage layout
1.3.5 | Task | Integrate authentication UI |  | 1.1 - User Authentication System
1.4 | Work Package | Testing & Quality Assurance |  | 1.3 - Frontend Development
1.4.1 | Task | Write unit tests |  | --
1.4.2 | Task | Perform integration testing |  | 1.4.1 - Write unit tests
1.4.3 | Task | User acceptance testing |  | 1.4.2 - Perform integration testing
1.4.4 | Task | Security testing |  | 1.4.2 - Perform integration testing
1.5 | Work Package | Deployment & Launch |  | 1.4 - Testing & Quality Assurance
1.5.1 | Task | Set up production environment |  | --
1.5.2 | Task | Deploy application |  | 1.5.1 - Set up production environment
1.5.3 | Task | Monitor initial launch |  | 1.5.2 - Deploy application
[Your ID] | [Level] | [Your deliverable/work package/task name] |  | [WBS ID - Task Name] or --
[Your ID] | [Level] | [Your deliverable/work package/task name] |  | [WBS ID - Task Name] or --
[Your ID] | [Level] | [Your deliverable/work package/task name] |  | [WBS ID - Task Name] or --
[Your ID] | [Level] | [Your deliverable/work package/task name] |  | [WBS ID - Task Name] or --
[Your ID] | [Level] | [Your deliverable/work package/task name] |  | [WBS ID - Task Name] or --

## D4
WBS ID | Level | Task/Work Package Name | Duration | Dependencies (WBS ID & Name)
1 | Deliverable | Customer Portal Website |  | --
1.1 | Work Package | User Authentication System |  | 1.2 - Database Design
1.1.1 | Task | Design login page wireframes |  | --
1.1.2 | Task | Implement password validation |  | 1.1.1 - Design login page wireframes
1.1.3 | Task | Create user registration form |  | 1.1.1 - Design login page wireframes
1.1.4 | Task | Build forgot password functionality |  | 1.1.2 - Implement password validation
1.2 | Work Package | Database Design & Setup |  | --
1.2.1 | Task | Design database schema |  | --
1.2.2 | Task | Create database tables |  | 1.2.1 - Design database schema
1.2.3 | Task | Set up database connections |  | 1.2.2 - Create database tables
1.2.4 | Task | Create test data |  | 1.2.2 - Create database tables
1.3 | Work Package | Frontend Development |  | 1.1 - User Authentication System
1.3.1 | Task | Create homepage layout |  | --
1.3.2 | Task | Build user dashboard |  | 1.3.1 - Create homepage layout
1.3.3 | Task | Implement responsive design |  | 1.3.2 - Build user dashboard
1.3.4 | Task | Add navigation system |  | 1.3.1 - Create homepage layout
1.3.5 | Task | Integrate authentication UI |  | 1.1 - User Authentication System
1.4 | Work Package | Testing & Quality Assurance |  | 1.3 - Frontend Development
1.4.1 | Task | Write unit tests |  | --
1.4.2 | Task | Perform integration testing |  | 1.4.1 - Write unit tests
1.4.3 | Task | User acceptance testing |  | 1.4.2 - Perform integration testing
1.4.4 | Task | Security testing |  | 1.4.2 - Perform integration testing
1.5 | Work Package | Deployment & Launch |  | 1.4 - Testing & Quality Assurance
1.5.1 | Task | Set up production environment |  | --
1.5.2 | Task | Deploy application |  | 1.5.1 - Set up production environment
1.5.3 | Task | Monitor initial launch |  | 1.5.2 - Deploy application
[Your ID] | [Level] | [Your deliverable/work package/task name] |  | [WBS ID - Task Name] or --
[Your ID] | [Level] | [Your deliverable/work package/task name] |  | [WBS ID - Task Name] or --
[Your ID] | [Level] | [Your deliverable/work package/task name] |  | [WBS ID - Task Name] or --
[Your ID] | [Level] | [Your deliverable/work package/task name] |  | [WBS ID - Task Name] or --
[Your ID] | [Level] | [Your deliverable/work package/task name] |  | [WBS ID - Task Name] or --